## SprintTracking
Sprint# | TimeFrame | Assignment | Task | Person
1 | Sept 24 - Sept 29 | Build a Skeleton Webservice and Deploy It | Create Single Table DB for Books. Fields: BookID, BookTitle,
1 | Sept 24 - Sept 29 | Build a Skeleton Webservice and Deploy It | Create API to handle basic HTTP requests to add book, remove book, query Book by ID, and Title
1 | Sept 24 - Sept 29 | Build a Skeleton Webservice and Deploy It | Create Functions to route API functions to Postgres Functions
1 | Sept 24 - Sept 29 | Build a Skeleton Webservice and Deploy It | Deploy to Heroku
1 | Sept 24 - Sept 29 | Build a Skeleton Webservice and Deploy It | Plan next sprint (Thursday)
1 | Sept 24 - Sept 29 | Build a Skeleton Webservice and Deploy It | Collect summaries and post Sprint review to group wiki (Thursday)

## Backlog
Task